## Task Planning Template
Table C47 Task Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 07/04/2016
| Project |  |  |  |  | Instructor | P. E. B. M
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 20.3477 | 16.69% | 20.3477 | 16.69% | 2016-04-07 | 2016-04-07 | 16.69% | 16.69%
2 | Design | 17.4 | 14.27% | 37.7477 | 30.97% | 2016-04-11 | 2016-04-12 | 14.27% | 30.97%
3 | Code | 37.4504 | 30.72% | 75.1981 | 61.69% | 2016-04-11 | 2016-04-12 | 30.72% | 61.69%
4 | Compile | 4.3857 | 3.598% | 79.5838 | 65.29% | 2016-04-12 | 2016-04-13 | 3.598% | 65.29%
5 | Test | 13.709 | 11.25% | 93.2928 | 76.54% | 2016-04-12 | 2016-04-13 | 11.25% | 76.54%
6 | Postmortem | 28.6017 | 23.46% | 121.8945 | 100% | 2016-04-13 | 2016-04-13 | 23.46% | 100%
Total |  | 121.8945 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 23/06/2016
| Project | List Sort, Programa 8A |  |  |  | Instructor | J. R. A. C.
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2016-06-23 | 40 | 40 | 42.55% | 0 | 0 | 0%
2 | 2016-06-24 | 40 | 80 | 85.11% | 0 | 0 | 0%
3 | 2016-06-25 | 20 | 100 | 106.4% | 0 | 0 | 0%
4 | 2016-06-26 | 0 | 100 | 106.4% | 0 | 0 | 0%
5
6
7