## Task Planning Template
Table C47 Task Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 2016-07-07
| Project | Chi-square Test 9A |  |  |  | Instructor | J. R. A. C.
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 42.2501 | 15.39% | 42.2501 | 15.39% | 2016-07-07 | 2016-07-07
2 | Design | 121.2458 | 44.17% | 163.4959 | 59.56% | 2016-07-08 | 2016-07-08
3 | Design Review | 23.2308 | 8.463% | 186.7267 | 68.03% | 2016-07-09 | 2016-07-09
4 | Code | 41.973 | 15.29% | 228.6997 | 83.32% | 2016-07-10 | 2016-07-10
5 | Code Review | 15.5467 | 5.664% | 244.2464 | 88.98% | 2016-07-11 | 2016-07-11
6 | Compile | 0.39406 | 0.1436% | 244.6404 | 89.13% | 2016-07-12 | 2016-07-12
7 | Test | 14.8633 | 5.415% | 259.5037 | 94.54% | 2016-07-13 | 2016-07-13
8 | Postmortem | 14.9802 | 5.458% | 274.484 | 100% | 2016-07-14 | 2016-07-14
Total |  | 274.484 | 100%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 2016-07-07
| Project | Chi-square Test 9A |  |  |  | Instructor | J. R. A. C.
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2016-07-07 | 42.2501 | 42.2501 | 15.39% | 0 | 0 | 0%
2 | 2016-07-08 | 121.2458 | 163.4959 | 59.56% | 0 | 0 | 0%
3 | 2016-07-09 | 23.2308 | 186.7267 | 68.03% | 0 | 0 | 0%
4 | 2016-07-10 | 41.973 | 228.6997 | 83.32% | 0 | 0 | 0%
5 | 2016-07-11 | 15.5467 | 244.2464 | 88.98%
6 | 2016-07-12 | 0.39406 | 244.6404 | 89.13%
7 | 2016-07-13 | 14.8633 | 259.5037 | 94.54%
| 2016-07-14 | 14.9802 | 274.484 | 100%