## Task Planning Template
Table C47 Task Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 2016-07-07
| Project | Chi-square Test 9A |  |  |  | Instructor | J. R. A. C.
Task |  | Plan |  |  |  |  | Actual
Number | Name | Minutes | Planned Value | Cumulative Minutes | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value
1 | Planning | 42.2501 | 15.39% | 42.2501 | 15.39% | 2016-07-07 | 2016-07-07 | 0% | 0%
2 | Design | 121.2458 | 44.17% | 163.4959 | 59.56% | 2016-07-08 | 2016-07-08 | 0% | 0%
3 | Design Review | 23.2308 | 8.463% | 186.7267 | 68.03% | 2016-07-09 | 2016-07-09 | 0% | 0%
4 | Code | 41.973 | 15.29% | 228.6997 | 83.32% | 2016-07-10 | 2016-07-10 | 0% | 0%
5 | Code Review | 15.5467 | 5.664% | 244.2464 | 88.98% | 2016-07-11 | 2016-07-11 | 15% | 15%
6 | Compile | 0.39406 | 0.1436% | 244.6404 | 89.13% | 2016-07-12 | 2016-07-12 | 0% | 15%
7 | Test | 14.8633 | 5.415% | 259.5037 | 94.54% | 2016-07-13 | 2016-07-13 | 0% | 15%
8 | Postmortem | 14.9802 | 5.458% | 274.484 | 100% | 2016-07-14 | 2016-07-14 | 0% | 15%
Total |  | 274.484 | 100% |  |  |  | 2016-07-15 | 67.93% | 82.93%
[7 empty] | 2016-07-16 | 11.22% | 94.15%
[7 empty] | 2016-07-17 | 0% | 94.15%
[7 empty] | 2016-07-18 | 0% | 94.15%
[7 empty] | 2016-07-19 | 5.458% | 99.61%

## Schedule Planning Template
Table C49 Schedule Planning Template
| Student | Juan Alberto Gutierrez Canto |  |  |  | Date | 2016-07-07
| Project | Chi-square Test 9A |  |  |  | Instructor | J. R. A. C.
|  | Plan |  |  | Actual
Day Number | Date Monday | Direct Min | Cumutative Minute | Cumulative Planned Value | Direct Min | Cumulative Minutes | Cumulative Earned Value | Adjusted Earned Value
1 | 2016-07-07 | 42.2501 | 42.2501 | 15.39% | 14.7 | 14.7 | 1.842% | 13.55%
2 | 2016-07-08 | 121.2458 | 163.4959 | 59.56% | 30.3 | 45 | 3.797% | 55.77%
3 | 2016-07-09 | 23.2308 | 186.7267 | 68.03% | 97.1 | 142.1 | 12.17% | 55.86%
4 | 2016-07-10 | 41.973 | 228.6997 | 83.32% | 0 | 142.1 | 0% | 83.32%
5 | 2016-07-11 | 15.5467 | 244.2464 | 88.98% | 30.2 | 172.3 | 3.784% | 85.2%
6 | 2016-07-12 | 0.39406 | 244.6404 | 89.13% | 97 | 269.3 | 12.15% | 76.97%
7 | 2016-07-13 | 14.8633 | 259.5037 | 94.54% | 49.6 | 318.9 | 6.215% | 88.33%
| 2016-07-14 | 14.9802 | 274.484 | 100% | 101.7 | 420.6 | 12.74% | 87.26%
[5 empty] | 208.8 | 629.4 | 26.16% | -26.16%
[5 empty] | 95.2 | 724.6 | 11.93% | -11.93%
[5 empty] | 73.5 | 798.1 | 9.209% | -9.209%
[5 empty] | 798.1 |  | 100% | -100%